## Project Tracker
Day | Date | Week | Phase | Task | What to Complete | Hours | Status | GitHub Commit? | Notes
1 | 2026-08-23 | Week 1 | Dataset Validation | Check duplicates, impossible/negative values, target correctness | Check duplicate commits, impossible/negative values, target correctness, and row-level sanity. | 1.5 | Done | Yes | V1.1 dataset validated: 153,994 commits, 0 duplicates, 0 missing values, target distribution verified. Extreme feature values identified; will be investigated during feature/outlier analysis before modeling.
2 | 2026-08-24 | Week 1 | Temporal Validation | Validate chronological ordering and previous_fault_count for leakage | Verify chronological ordering and that historical features never use future information. | 1.5 | Done | Yes
3 | 2026-08-25 | Week 1 | Feature Analysis | Inspect distributions, outliers, and suspicious feature values | Inspect distributions, outliers, skew, zero values, and suspicious feature ranges. | 1.5 | Done | Yes
4 | 2026-08-26 | Week 1 | Baseline Dataset | Finalize the clean V1 baseline dataset | Freeze the validated baseline feature schema and create the research-ready dataset. | 1.5 | Not Started | No
5 | 2026-08-27 | Week 1 | Train/Test Strategy | Design time-aware/project-aware split and leakage safeguards | Use time-aware/project-aware evaluation; define train/validation/test boundaries. | 1.5 | Not Started | No
6 | 2026-08-28 | Week 1 | Preprocessing | Build reproducible preprocessing pipeline | Create reproducible preprocessing for numeric/categorical features and imbalance handling. | 1.5 | Not Started | No
7 | 2026-08-29 | Week 1 | Milestone 1 | Baseline dataset ready; document methodology and commit to GitHub | Document baseline dataset methodology and push milestone to GitHub. | 2 | Not Started | Yes
8 | 2026-08-30 | Week 2 | Baseline ML | Train Logistic Regression baseline | Train a simple interpretable baseline. | 1.5 | Not Started | No
9 | 2026-08-31 | Week 2 | Baseline ML | Train Random Forest | Train Random Forest and record metrics. | 1.5 | Not Started | No
10 | 2026-09-01 | Week 2 | Baseline ML | Train XGBoost | Train XGBoost and record metrics. | 1.5 | Not Started | No
11 | 2026-09-02 | Week 2 | Evaluation | Evaluate precision, recall, F1, ROC-AUC, PR-AUC, confusion matrix | Use precision, recall, F1, ROC-AUC, PR-AUC and confusion matrix; don't rely on accuracy. | 2 | Not Started | No
12 | 2026-09-03 | Week 2 | Class Imbalance | Handle imbalance only within training data and compare results | Compare class weighting/resampling while preventing leakage. | 1.5 | Not Started | No
13 | 2026-09-04 | Week 2 | Baseline Analysis | Compare models and perform error analysis | Compare models and inspect false positives/false negatives. | 2 | Not Started | No
14 | 2026-09-05 | Week 2 | Milestone 2 | Finalize baseline model/results and commit to GitHub | Freeze baseline experiment and push code/results documentation. | 2 | Not Started | Yes
15 | 2026-09-06 | Week 3 | Refactoring | Build refactoring-enhanced feature dataset | Add has_refactoring, count and type-count features. | 1.5 | Not Started | No
16 | 2026-09-07 | Week 3 | Refactoring | Train and evaluate Model 2 | Train/evaluate refactoring-enhanced model. | 1.5 | Not Started | No
17 | 2026-09-08 | Week 3 | Comparison | Measure improvement over baseline | Quantify improvement over baseline. | 1.5 | Not Started | No
18 | 2026-09-09 | Week 3 | Sonar | Build temporally aligned Sonar quality/technical-debt features | Align Sonar measurements to information available before each prediction commit. | 2 | Not Started | No
19 | 2026-09-10 | Week 3 | Sonar | Train and evaluate Model 3 | Train/evaluate quality + technical-debt enhanced model. | 2 | Not Started | No
20 | 2026-09-11 | Week 3 | Research Analysis | Compare all models and analyze whether added features help | Answer whether progressively adding features improves prediction. | 2 | Not Started | No
21 | 2026-09-12 | Week 3 | Research Analysis | Document findings, limitations, and research implications | Record research findings, limitations, and implications. | 1.5 | Not Started | No
22 | 2026-09-13 | Week 4 | Milestone 3 | Finalize experiments and commit results/code to GitHub | Freeze experimental results and push milestone. | 2 | Not Started | Yes
23 | 2026-09-14 | Week 4 | Explainability | Implement SHAP | Implement SHAP on final model. | 1.5 | Not Started | No
24 | 2026-09-15 | Week 4 | Explainability | Analyze global and individual feature importance | Identify global and per-commit risk drivers. | 1.5 | Not Started | No
25 | 2026-09-16 | Week 4 | Explainability | Generate human-readable risk explanations | Turn model explanations into understandable risk reasons. | 1.5 | Not Started | No
26 | 2026-09-17 | Week 4 | Real-World Pipeline | Build prediction pipeline for an unseen/new commit | Accept a new/unseen commit and produce a risk score. | 2 | Not Started | No
27 | 2026-09-18 | Week 4 | Real-World Testing | Test on an unseen repository/time period | Evaluate generalization on an unseen repository or future time period. | 2 | Not Started | No
28 | 2026-09-19 | Week 4 | Recommendations | Generate actionable predictive-maintenance recommendations | Translate risk factors into actionable maintenance suggestions. | 1.5 | Not Started | No
29 | 2026-09-20 | Week 5 | Final Integration | Integrate prediction + explanation + recommendation pipeline | Connect prediction, explanation and recommendation components. | 2 | Not Started | No
30 | 2026-09-21 | Week 5 | GitHub & Docs | Polish README, architecture, methodology, setup and experiment documentation | Polish README, architecture, setup, methodology and experiment documentation. | 2 | Not Started | Yes
31 | 2026-09-22 | Week 5 | Final Review | Review reproducibility, leakage, metrics, limitations and claims | Final audit for leakage, reproducibility, metrics, limitations and overclaiming. | 2 | Not Started | No
32 | 2026-09-23 | Week 5 | Final GitHub | Final cleanup and final meaningful commit | Final GitHub cleanup and meaningful final commit. | 1.5 | Not Started | Yes
33 | 2026-09-24 | Week 5 | Buffer | Fix unexpected issues / rerun experiments | Use only if needed for unexpected technical/research issues. | 2 | Not Started | No
34 | 2026-09-25 | Week 5 | Buffer | Final paper/report preparation and presentation notes | Prepare final paper/report and presentation explanation. | 2 | Not Started | No

## Progress
AI-Assisted Software Evolution & Predictive Maintenance
Total tasks | 34
Completed | 3
In Progress | 0
Blocked | 0
Overall completion | 8.824%
Current milestone | Dataset validation
Important | Commit meaningful milestones to GitHub regularly. Never upload td_V2.db or generated datasets.